## Sheet1
ET Priority List
Station | What | When | Priority | Help Needed? | Status
MVNC | 2nd Noise Survey & Install | Jan 2016 | 1 | No | Move Test equipment and re-test.
VHTN | Replace both horizontal S-13s | ? | 2 | Yes
BCRT | Replace/Re-Level N-S Sensor | Jan 2016 | 3 | No
CMGA | Larger solar panels, more/larger batteries. Replace N-S sensor? | ? | 4 | ?
GMG | Pit site going down at night and back in day with good batteries and 2 panels. Do we need more? | ? | 5 | ?
CPRT | Replace accelerometer. Repoint antenna to cttn. | ? | 6 | No
cttn | Install equipment from svfd to make this the new internet drop for CPRT. | ? | 7 | Yes | Mast installed
svfd | Decommission and move to cttn. | ? | 8 | Yes
gttn | Decommission | ? | 9 | Yes
PMTN | Find replacement site and install. |  | 10 | Yes
hpnc | Finish installation. Probably won't happen until late winter early spring. |  | 11 | Yes
TZTN | Cover instruments. Replace Strong Motion. |  | 12 | No
TRYN | Install S-13's. Add second ground rod at pit, replace power supply with BC-12. Add line amp. |  | 13 | Yes
MGNC | S-13 upgrade. |  | 14 | ?
TVNC | S-13 upgrade. Move the pit to the edge of the woods. Replace balanced line and put in conduit. Add line amp. |  | 15 | Yes
GFM | Find new, more accessible site. Noise study. Install |  | 16 | Yes
fgtn | Repair/rebuild cab hatch. Cameras? |  | 17 | No
WSNC | New batteries. |  | 18 | No
ATTN | Cover AC inputs at bottom of indoor boxes for safety when we ask someone locally to reset. |  | 19 | No
SHTN | Cover AC inputs at bottom of indoor boxes for safety when we ask someone locally to reset. |  | 20 | No
CVVA | Cover AC inputs at bottom of indoor boxes for safety when we ask someone locally to reset. |  | 21 | No
CSTN | Remove router. Cover AC inputs at bottom of indoor boxes for safety when we ask someone locally to reset. |  | 22 | No
ETT | Waterproof or replace box. Add 2nd ground rod. |  | 23 | No
CPCT | Figure out how to keep rodents from chewing the cables. |  | 24 | ?
GRBT | Replace balanced line and put in conduit. |  | 25 | No
385 | Repair CB & Ham radios. |  | 26 | No
LRVA | Install Line amp to adjust audio levels into transmitter |  | 27 | No
SWET Belltower | Replace existing phone line with either fiber or twisted pair. Install missing surge suppressor. Cover power supply. Replace Battery. |  | 28 | No
WMTN | Upgrade SP to 53W. Move pit. Re-test digital link to ASTN. Repair/replace cab door and hasp. |  | 29 | Yes
CCNC | Install Line amp to adjust audio levels into transmitter |  | 30 | No
RCGA | New AC power source, existing cable is dangerous. Install terminal strips for pit box and power supply box. Change balun at pit box. Install coax bulkhead for feed line and close up hole in cabinet. Roll roofing on shed? Replace windows on shed? Clean out shed. Surge suppression on AC power coming in. Get key to deer park. |  | 31
Starr Mtn. | Remove unneeded antennas. Paint tower? |  | 32 | No
McMinn EMA |  |  | 33
GMG |  |  | 34
FPAL |  |  | 35
SWET |  |  | 36
DYTN | Replace N-S sensor? |  | 37
mttn |  |  | 38
NCCU |  |  | 39
wbtn |  |  | 40
Completed jobs.
GFM | Isis 4 upgrade. Maybe Re-point antenna to hpnc. | Nov. 2015 | 1 | No | Done
CCNC | S-13 upgrade. Test Digital link to ASTN Install line amp to adjust audio into Tx. | Nov. 2015 | 2 | Probably | Done
SMNC | S-13 upgrade, Replace balanced line, improve grounding at each end, replace power supply with BC-12. | Nov. 2015 | 4 | Yes | Done
BCRT | Replace SM vault and instrument. Improve grounding. Install new backup battery to RT-130. | ? | 11 | ? | Done
At least one component down or mission critical problem.
High priority but station more or less working OR this is coming up soon.
Medium priority but don't forget, can wait until maintenance visit.
Low priority or no issues.
Job Done.