## Sheet1
ET Priority List
Station | What | When | Priority | Help Needed? | Status
RCGA | Isis 4 polarity repair. New AC power source, existing cable is dangerous. Install terminal strips for pit box and power supply box. Change balun at pit box. Install coax bulkhead for feed line and close up hole in cabinet. Roll roofing on shed? Replace windows on shed? Clean out shed. Surge suppression on AC power coming in. Get key to deer park. | Dec 2016 | 1 | Yes
CMGA | Larger solar panels, more/larger batteries, cut trees. | Dec 2016 | 3 | ?
BCRT | Replace/Re-Level N-S Sensor | Jan 2016 | 2 | No
GRBT | Repair E-W problem. Replace balanced line and put in conduit. | Jan 2016 | 4 | No
DYTN | Repair Z problem. | Jan 2016 | 5 | No
MVNC | 3rd Noise Survey & Install | Spring 2017 | 6 | No | Move Test equipment and re-test.
CVVA | Install hardware allowing use of dynamic IP addressing. Eventually move vault to open area further away from the building. Cover AC inputs at bottom of indoor boxes for safety when we ask someone locally to reset. | Winter - Spring 2017 | 7 | No
cort | Upgrade to be able to communicate even with dynamic IP addressing. | Spring 2017 | 8 | No
GFM2 | Install | Spring 2017 | 9 | Yes
hpnc | Replace power supply. Finish installation. |  | 10 | Yes
TZTN | Cover instruments. | Spring 2017 | 11 | No
GFM | Remove |  | 12 | Yes
fgtn | Cameras? |  | 13 | No
WSNC | New batteries. |  | 14 | No
gttn | Remove tower hardware. |  | 15 | Yes
ATTN | Cover AC inputs at bottom of indoor boxes for safety when we ask someone locally to reset. |  | 16 | No
SHTN | Cover AC inputs at bottom of indoor boxes for safety when we ask someone locally to reset. |  | 17 | No
CSTN | Remove router. Cover AC inputs at bottom of indoor boxes for safety when we ask someone locally to reset. |  | 18 | No
ETT | Add 2nd ground rod. |  | 19 | No
385 | Repair/Replace CB & Ham radios. |  | 20 | No
SWET Belltower | Replace existing phone line with either fiber or twisted pair. Install missing surge suppressor. Cover power supply. Re-terminate LMR200 N connector at box. |  | 21 | No
WMTN | Move pit. Re-test digital link to ASTN. Repair/replace cab door and hasp. |  | 22 | Yes
Etowah Utilities | Install equipment to establish microwave link between EU and Starr Mountain. Create secondary data path and move camera data to this connection. |  | 23 | Yes
Starr Mtn. | Remove unneeded antennas. Paint tower? |  | 24 | No
GMG |  |  | 25
FPAL |  |  | 26
SWET |  |  | 27
mttn |  |  | 28
NCCU |  |  | 29
wbtn |  |  | 30
Completed jobs.
GFM | Isis 4 polarity issue repaired. |  | 1 | No | Done
CCNC | S-13 upgrade. Isis 4 polarity issue repaired. Test Digital link to ASTN Install line amp to adjust audio into Tx. |  | 2 | Probably | Done
TRYN | S-13 upgrade. Isis 4 polarity repair. Added line amp. |  | 3 |  | Done
SMNC/ DSNC | S-13 upgrade, Relocated Pit. |  | 4 | Yes | Done
TVNC | Moved pit to create TVNC2. S-13 Upgrade, Isis 4 polarity repair. Balanced line in conduit. Added line amp. |  | 5 |  | Done
CPRT | Replaced E-W and strong motion instruments. Re-established internet link at cort. |  | 6 |  | Done
cort | Installed |  | 7 |  | Done
BCRT | Replaced Strong Motion vault. Releveled N-S instrument, Replaced E-W instrument, replaced Strong Motion instrument. Installed new RT-130 battery. Improved grounding. |  | 8 |  | Done
CCRT | Isis 4 polarity repair. |  | 9 |  | Done
DYTN | Replace N-S sensor? |  | 10 |  | Done
ETT | Isis 4 polarity repair. |  | 11 |  | Done
GMG | Added panel and battery at pit site. BC10. |  | 12 |  | Done
MGNC | S-13 upgrade. Isis 4 polarity repair. |  | 13 |  | Done
LRVA | Isis 4 polarity repair. Installed line amp. |  | 14 |  | Done
McMinn EMA | Decommissioned |  | 15 |  | Done
VHTN | Replaced both horizontal S-13s. Isis 4 polarity problem repaired. |  | 16 |  | Done
svfd | Decommissioned |  | 17 |  | Done
gttn | Decommissioned |  | 18 |  | Done
WMTN | Repaired Isis 4 polarity issue. |  | 19 |  | Done
TZTN | Replaced strong motion instrument. Re-orented broadband. |  | 20 |  | Done
GRBT | Repaired Isis 4 polarity issue. |  | 21 |  | Done
At least one component down or mission critical problem.
High priority but station more or less working OR this is coming up soon.
Medium priority but don't forget, can wait until maintenance visit.
Low priority or no issues.
Job Done.